## Sheet1
HINDUSTAN COPPER LIMITED
TALOJA COPPER PROJECT
Tender No | Item / Nature of work | Mode of tender enquiry | Date of Publication of NIT | Type of bidding single / two bid system | Last date of receipt of tender | No. of offers received | Nos. & name of parties qualified after technical evaluation | Nos. & name of parties not qualified after technical evaluation | Whether contract awarded to lowest tenderer/evaluated L1 | Contract No. & Date | Name of Contractor / party | Value of contract (Rs. In lakhs INCLUSIVE OF TAXES) | Scheduled date of completion of supplies | Actual date of start of work | Actual date of comp-letion | Reasons for delay if any
1636 | REPAIR CIVIL JOBS | OPEN | 2018-03-04 | DOUBLE | 2018-08-05 | 2 | 02- R.S. DEVLOPERS YOJANA CONSTRUCTIONS | - | YES | 2820 DT. 26/06/2018 | R.S. DEVELOPERS | 21.08 | 31/07/2019 | 2018-07-01 | UNDER PROGRESS | -
1587 | SUPPLY OF COMPRESSED OXYGEN GAS IN STANDARD OXYGEN CYLINDER FILLED IN 6 TO 7 CU.M. GAS, CONFIRM TO IS:309-92 PRESSURE 140 KG/SQ. CM MINIMUM. | OPEN | 27/12/2017 | DOUBLE | 19/02/2018 | 4 | 02- SANGHI UDYOG AA TRADERS | 2 | YES | 2775 DT 28/04/2018 | SANGHI UDYOG | 3.54 | 30/04/2019 | 2018-05-01 | UNDER PROGRESS | -
1602 | SUPPLY OF STRAPPING CLIPS SIZE : 57MM L x 0.92MM THICK(SUITABLE FOR STRAPPING 1 1/4" WIDTH x 0.65MM THICK OUTSIDE RED COLOUR PAINTED WITH HINDCOP ROD IN BLACK COLOUR | OPEN | 2018-09-02 | DOUBLE | 19/03/2018 | 2 | 02- SIGNODE INDIA PVT LTD WALZEN STRIP PVT LTD | - | YES | 2779 DT 21/04/2018 | SIGNODE INDIA PVT LTD | 3.01 | 31/05/2019 | 2018-04-01 | UNDER PROGRESS | -
1637 | SUPPLY OF LUBEWELL HR-AL HOT ROLLING COMPOUND | STE (OEM) | 2018-05-04 | SINGLE | 13/04/2018 | 1 | RICHARDS APEX AUSTRALIA | - | YES | 2798 DT 05/05/2018 | RICHARDS APEX AUSTRALIA | 12.01 | 2018-01-10 |  | UNDER PROGRESS | -
1639 | DISMANTLING OF EXISTING SHED & CONSTRUCTION OF NEW SHED IN BETWEEN COOLING TOWER – 1 AND 2 | OPEN | 2018-12-04 | DOUBLE | 14/05/2018 | 2 | 02- R.S. DEVLOPERS B.M. CONSTRUCTIONS | - | YES | 2824 DT 26/06/2018 | B.M. CONSTRUCTIONS | 15.74 | 31/10/2018 | 2018-07-01 | UNDER PROGRESS | -
1641 | LIGHTING TOWERS & MISCELLANEOUS JOB. | OPEN | 2018-03-04 | DOUBLE | 26/05/2018 | 2 | 02- B.M. CONSTRUCTION R.S. DEVELOPERS | - | YES | 2826 DT 27/06/2018 | R.S. DEVELOPERS | 5.97 | 31/12/2018 | 2018-07-01 | UNDER PROGRESS | -
1586 | REPAIR & MAINTENANCE OF PL-6 FLATS | OPEN | 18/12/2017 | DOUBLE | 22/01/2018 | 3 | 03 - RS DEVELOPERS, SHAKTI CONSTRUCTION YOJANA CONSTRUCTIONS | - | YES | 2841 DT 04/07/2018 | SHAKTI CONSTRUCTIONS | 29.39 | 29/09/2018 | 2018-07-01 | STILL UNDER PROGRESS | -